## Jira Stories
Key | Type | Component | Title | Est. Hours | Description
| Story | global search bar | Document completed Global Search POC baseline for SPACE integration | 4 | Capture what is already live in the Global Search POC so SPACE integration does not re-do that work. Already done: - Multi-source search (BuildTrack, Assets, Space Action + sibling Space DBs) - Azure AI Search as discovery layer; SQL as source of truth; Top-K + LLM answers - Space Action schema-aware indexing (action.* tables, text columns only; excluded OfflineSyncLog / Synonyms_Configuration; ~6.6k docs in space-action-index) - Production flags: hydrate from SQL, catalog, incremental sync, security trim, metrics - Space ProjectId cross-DB hops (Project, HSE, Incident, LMS, CMS, Dashboard) - SearchBar types + Linked badge for related Space records - APIs: POST /api/search/results, POST /api/search/answer, GET /api/search/sources - Widget client under frontend/lib/global-search (createSearchClient) Deliverable: 1-page baseline note for SPACE app team (architecture, sources, APIs).
| Story | global search bar | Agree SPACE embed strategy: widget vs iframe vs shared package | 8 | Workshop with SPACE application team to pick how Global Search Bar is hosted. Decide: - Embed SearchBar in SPACE header (shared React) vs iframe vs copy of lib/global-search - Auth: reuse SPACE session / SSO vs pass JWT to Global Search API - API base URL, CORS, DEV vs UAT vs PROD - Which Space SQL databases must be on for go-live (Action, Project, HSE, etc.) Deliverable: short integration design (embed choice, auth, env matrix).
| Story | global search bar | Freeze Global Search API contract for SPACE host app | 6 | Publish a stable contract SPACE can call without depending on BuildTrack UI. Include: - POST /api/search/results (fast hits, no LLM) - POST /api/search/answer (Top-K + AI summary) - GET /api/search/sources - Request fields: query, filter_type, top_k, source_ids - Response fields: results[], metadata.database_id, content_type, url, score - Auth header (Bearer) and 401/422/503 behaviour Deliverable: API contract page + example payloads SPACE can implement against.
| Story | global search bar | Package SearchBar as reusable module with SPACE-ready props | 8 | Extract frontend/lib/global-search so SPACE can mount it without forking BuildTrack. Props/config: - apiBaseUrl, getAuthToken, theme tokens (SPACE colours) - contentTypes map (project, event, HSE, incident, document, etc.) - onOpenResult callback for SPACE routing - source_ids default for SPACE-only search Deliverable: reusable SearchBar module + README for SPACE developers.
| Story | global search bar | Map SPACE session user into search security and project scope | 8 | Wire SPACE logged-in user into Global Search so results respect SPACE permissions. Work: - Pass SPACE JWT/session token to GET/POST /api/search/* - Map user id / roles to search security_trim (project membership) - Pass active SPACE project/company as filter so queries are scoped - Fail closed on missing token; document empty vs forbidden states Deliverable: auth mapping table + working DEV login from SPACE shell.
| Story | global search bar | Mount Global Search Bar in SPACE application shell (DEV) | 8 | Embed Global Search Bar in SPACE header/shell on DEV. Work: - Place bar in SPACE chrome (header or command palette) - Match SPACE visual tokens where required - Point to Global Search API DEV (Space SQL via VPN / on-prem) - Smoke test: inspection / EVT number / list active projects / Linked hops Deliverable: SearchBar visible and usable inside SPACE DEV.
| Story | global search bar | Deep-link search results into SPACE module screens | 8 | Clicking a search result must open the correct SPACE screen, not BuildTrack routes. Map hit types to SPACE URLs, including: - space-project / project → SPACE project page - event / event_agenda / event_task → SPACE Action/event screens - HSE occupational/environmental review → SPACE HSE - incident → SPACE Incident - employment / LMS → SPACE LMS - contract / CMS → SPACE CMS - documents / DMS / attachment → SPACE DMS where keys exist Deliverable: url mapper + verified clicks for top content types.
| Story | global search bar | Harden Space ProjectId / DocumentId hops for SPACE demo queries | 6 | POC already hops ProjectId across Project, HSE, Incident, LMS, CMS, Dashboard. For SPACE integration, lock demo queries and fill remaining high-value hops. Work: - Regression pack: list active projects, HSE reviews, incidents, contracts, EVT/agenda - Add DocumentId hop (DMS/Attachment ↔ project) where FKs exist - Reduce duplicate schema_sql vs space_project cards in UI - Document which of 17 Space DBs are searchable vs hop-only Deliverable: demo query list + expected Linked badges.
| Story | global search bar | Deploy Global Search API for SPACE DEV with runbook | 8 | Stand up Global Search API for SPACE DEV (and note UAT path). Work: - Env: Space SQL URLs, Azure AI Search indexes, Azure OpenAI, CORS for SPACE origin - Schema catalog / space-index sync runbook (POST /api/search/space-index) - Health: /api/health, /api/search/space-index/status, /api/search/sources - Secrets: Key Vault or equivalent; no keys in SPACE frontend - One-process-per-port notes (avoid duplicate uvicorn on 8000) Deliverable: DEV deploy + 1-page runbook for SPACE ops.
| Story | global search bar | SPACE UAT checklist, latency baseline, and go/no-go for 31 Aug | 8 | UAT and readiness checkpoint before 31-Aug-2026. Work: - Checklist: login from SPACE, results, AI answer, Linked hops, empty query, 401 - Measure /search/results vs /search/answer latency on SPACE DEV - Fix P1 UAT issues (auth, CORS, wrong deep-links, missing Space source) - Go/no-go: CORS, VPN/SQL, flags, rollback, demo script for manager - Backlog after 31 Aug: UserId hops, BMS name match, UAT/PROD full rollout Deliverable: UAT report + go/no-go note dated on or before 31 Aug.

## Integration Plan to 31 Aug
Global Search Bar → SPACE application — plan through 31 Aug 2026
When | Focus | Stories (titles) | Hours
Already done (before this sprint) | POC search + Space data + ProjectId hops | Document completed Global Search POC baseline for SPACE integration | 4
20–22 Aug | Design + API + widget package | Agree embed strategy; Freeze API contract; Package SearchBar module | 22
24–26 Aug | Auth + embed in SPACE DEV | Map SPACE session into search; Mount SearchBar in SPACE shell (DEV) | 16
27–28 Aug | Deep-links + demo hops | Deep-link into SPACE modules; Harden ProjectId/DocumentId hops | 14
29–31 Aug | Deploy + UAT + go/no-go | Deploy API for SPACE DEV; UAT checklist, latency, go/no-go by 31 Aug | 16
Total estimated hours (10 stories): 72
Type = Story for all rows. Component = global search bar. Key left blank (optional).
Out of scope until after 31 Aug: full UAT/PROD rollout, UserId graph hops, BMS name-match, re-enabling BuildTrack/Assets inside SPACE if not required for MVP.