## Global Search Worklog
Ticket ID | Component | Log Date | Day | Hours | Phase | Title | Task Description | Status
GS-SPACE-01 | global search bar | 2026-08-17 | Mon | 2 | Space Cross-DB Linking | ProjectId hub design & key promotion | Defined Space cross-DB linking hub on numeric ProjectId. Promoted ProjectId/UserId/DocumentId (and project name) from schema-SQL rows onto hit metadata in executor so related DBs can join on the same key. | Done
GS-SPACE-02 | global search bar | 2026-08-17 | Mon | 2.5 | Space Cross-DB Linking | Cross-DB ProjectId hop fetchers (6 Space DBs) | Implemented ProjectId hop fetchers in cross_db_links for Space Project, HSE (occupational + environmental reviews), Incident, LMS Employment, CMS ProjectCM, and Dashboard_Project_Details. Wired attach into multi-DB retrieve (including single Space source when siblings enabled). | Done
GS-SPACE-03 | global search bar | 2026-08-17 | Mon | 1.5 | Space Cross-DB Linking | Display filter + SearchBar for linked Space types | Fixed UI dropping linked hops: merge space_project_id related hits after answer/entity filters; added SearchBar TYPE_CONFIG for space_project, occupational/environmental review, incident, employment, contract, dashboard_project; stopped collapsing Space linked groups; Linked badge for related_via=space_project_id. | Done
GS-SPACE-04 | global search bar | 2026-08-17 | Mon | 1.5 | Space Cross-DB Linking | SQL join-key injection (ProjectId in SELECT) | Root-cause fix: LLM SQL for 'list active projects' omitted ProjectId. Validator now injects primary/join keys (ProjectId/UserId/DocumentId); generator prompt updated; related-hit budget and result slice increased. Verified ~34 linked results across types in UI. | Done
GS-SPACE-05 | global search bar | 2026-08-17 | Mon | 0.5 | Space Cross-DB Linking | E2E verification & manager walkthrough prep | Verified live /search/results and /search/answer for list active projects (ProjectIds + LINKED HSE/Incident/LMS/CMS). Documented which of 17 Space DBs are searchable vs ProjectId-linked for planning. | Done
GS-SPACE-06 | global search bar | 2026-08-18 | Tue | 4 | POC Hardening | Expand ProjectId hops + regression test pack | Add more ProjectId-linked tables where FKs exist; write a small regression pack (project list, HSE reviews, incidents, contracts) and document expected Linked badges / counts for demos. | Planned
GS-SPACE-07 | global search bar | 2026-08-19 | Wed | 4 | POC Hardening | DMS / DocumentId linking (deferred hop) | Design and implement DocumentId-based linking between Space DMS/Attachment and related project context so document queries can show Linked project/HSE where keys exist. | Planned
GS-SPACE-08 | global search bar | 2026-08-20 | Thu | 4 | POC Hardening | UserId graph linking (deferred hop) | Promote and hop on UserId across UM / LMS / Action where safe; keep permission boundaries clear for client readiness. | Planned
GS-SPACE-09 | global search bar | 2026-08-21 | Fri | 4 | POC Hardening | Answer quality & Linked UX polish | Tune AI answer citations for related_via=space_project_id; improve SearchBar grouping/tabs for Space content types; reduce duplicate schema_sql vs space_project cards where possible. | Planned
GS-SPACE-10 | global search bar | 2026-08-22 | Sat | 4 | POC Hardening | Security trim + source toggles review | Review security trimming for Space SQL results; confirm SEARCH_ENABLE_* flags and disable unused sources; document which DBs must be on for client demo. | Planned
GS-SPACE-11 | global search bar | 2026-08-25 | Tue | 8 | SPACE Client Integration | Integration design with SPACE app team | Align with SPACE (client) app architecture: embed vs iframe vs shared React package; auth (JWT/SSO/session cookie); API base URL; CORS; environment matrix (DEV/UAT/PROD). Produce short integration design note for manager. | Planned
GS-SPACE-12 | global search bar | 2026-08-26 | Wed | 8 | SPACE Client Integration | Extract reusable Global Search Bar package/API contract | Package SearchBar + API client as a reusable module (props: apiUrl, auth token, theme hooks). Freeze request/response contract for /search/results and /search/answer used by SPACE host app. | Planned
GS-SPACE-13 | global search bar | 2026-08-27 | Thu | 8 | SPACE Client Integration | Auth & tenant/project context wiring | Map SPACE logged-in user into search security context; pass active project/company filters into search so results respect SPACE session scope. | Planned
GS-SPACE-14 | global search bar | 2026-08-28 | Fri | 8 | SPACE Client Integration | Embed Global Search Bar into SPACE shell (DEV) | Mount Global Search Bar in SPACE application header/shell on DEV; match SPACE visual tokens where required; smoke-test list/filter queries against on-prem Space SQL. | Planned
GS-SPACE-15 | global search bar | 2026-08-29 | Sat | 6 | SPACE Client Integration | Deep-link results into SPACE modules | Map search hit types (project, HSE review, incident, employment, contract, document) to SPACE route URLs so clicking a result opens the correct SPACE screen. | Planned
GS-SPACE-16 | global search bar | 2026-09-01 | Tue | 8 | SPACE Client Integration | Backend deploy for SPACE environments | Deploy Global Search API (schema catalog sync, Azure OpenAI/AI Search config, Space SQL connectivity) for SPACE DEV/UAT; runbook for schema sync and health checks. | Planned
GS-SPACE-17 | global search bar | 2026-09-02 | Wed | 6 | SPACE Client Integration | UAT test plan + performance baseline | Write UAT checklist (queries per module, Linked hops, auth failures, empty states). Measure latency for /results vs /answer; set target SLAs for demo. | Planned
GS-SPACE-18 | global search bar | 2026-09-03 | Thu | 8 | SPACE Client Integration | UAT fixes & Linked hop coverage gaps | Fix UAT findings; add remaining high-value ProjectId (or DocumentId/UserId) hops requested by SPACE product owners. | Planned
GS-SPACE-19 | global search bar | 2026-09-04 | Fri | 4 | SPACE Client Integration | Manager demo pack & handover | Prepare demo script (active projects → Linked HSE/Incident/LMS), architecture one-pager (17 Space DBs + ProjectId hub), and backlog for post-go-live (BMS name match, Action/DMS linking, BuildTrack re-enable if needed). | Planned
GS-SPACE-20 | global search bar | 2026-09-05 | Sat | 8 | SPACE Client Integration | SPACE UAT/PROD readiness checkpoint | Final config review (env flags, secrets, CORS, VPN/SQL access), rollback plan, and go/no-go checklist with manager before wider SPACE rollout. | Planned

## Plan Summary
Global Search Bar → SPACE Client — Plan Summary
Section | Item | Hours | Notes
Completed (17-Aug-2026) | Space ProjectId cross-DB linking + UI/SQL fixes | 8 | Verified in BuildTrack POC UI: ~34 linked results
Near-term | POC hardening (hops, DocumentId/UserId, UX, security) | 20 | 18–22 Aug (indicative — adjust with manager)
Future | Integrate Global Search Bar into SPACE client app | 72 | Design → embed → deep-link → UAT → readiness
Total (this sheet) | All tickets GS-SPACE-01 … 20 | 100 | Dates are planning estimates
Data connected today | 17 Space DBs searchable; 6 in ProjectId hub | - | Project, HSE, Incident, LMS, CMS, Dashboard
Later backlog | BMS name match, Action/DMS deep link, BuildTrack/Assets re-enable | - | After SPACE embed MVP
Component for all task rows: "global search bar"
Prepared for manager planning — integrate Global Search Bar into SPACE application (client).