## Jira Stories
Key | Type | Component | Title | Est. Hours | Description
| Story | AI/ML | Review the Global Search POC and confirm what can be reused for SPACE | 4 | Date: 21-Aug-2026 (Fri). Went through the full POC and traced one real query end to end, so we know exactly what we are carrying into SPACE and what we are leaving behind. What the POC is today: - FastAPI backend, Next.js frontend, Azure AI Search, Azure OpenAI, Azure Blob. - It opens 19 direct SQL connections (BuildTrack, Assets and 17 SPACE databases). - No LangChain or LangGraph is used, so the new work must not be planned around one. Reuse (this is the real value in the POC): - Query understanding and query planner - rule based, fast, no LLM call. - Ranking logic - the hand-tuned boosts are the actual search intelligence. - Hybrid search - keyword plus meaning plus vector, run together. - Azure index design, the catalog pattern, and the incremental sync (only re-embeds rows that actually changed, so it controls cost). Do not reuse, with the reason: - The POC's own login - it would create a second login next to SPACE. - The 19 direct database connections - they ignore who is searching. - The LLM-writes-SQL feature - it runs generated SQL on live data, on the typing path. - In-memory caches - not per user and do not work with more than one server. - Backend-generated page links - the frontend should own its own routes. Bottom line: about 25-30 percent of the POC is worth carrying forward.
| Story | AI/ML | Check user permissions and security in the POC search path | 4 | Date: 21-Aug-2026 (Fri). Checked whether the POC can safely show different results to different users. This decides whether we can build on it or have to design fresh. Main findings: - Only two permission checks exist in the whole project, and the real one is switched off in the current setup. So no permission filtering runs today. - Two users with different access get exactly the same results. - The result cache does not include the user, so one user's results can be shown to another user for up to 2 minutes. - One place does check permission but then ignores the answer and keeps the row. - The AI answer is written from unfiltered results, so it can describe records the user is not allowed to see. - Reindex and clear-cache endpoints can be called by any logged-in user. - Live database passwords and Azure keys are sitting in backend/.env. Why this matters for the integration: this cannot be added on later as a wrapper. Permissions decide the index design, the cache key and how we call each module, so the permission model has to be agreed before any code is written. Immediate action: rotate every credential in backend/.env.
| Story | AI/ML | Finalise Global Search architecture for SPACE and confirm module readiness | 8 | Date: 24-Aug-2026 (Mon). Compared the possible designs, picked one, and checked which SPACE modules are actually ready to be searched. Options compared: search from the browser, search through the module APIs, search only through Azure AI Search, or a mix of API and index. Decision - use the mix: - Normal records (projects, incidents, meetings) are fetched live from the existing module APIs using the user's own login, so each module applies its own rules and our search can never be more permissive than the module itself. - Long text (contracts, documents, drawings) goes through Azure AI Search, because no module API will full-text search a 2000 character contract clause or a PDF. Here the server always adds the permission filter, and the user cannot change it. - A separate Global Search service, not a module inside an existing API, because it needs its own timeout budget and its own indexing job. - No user search will ever touch a database directly. Why not query the SPACE databases directly (the question we will be asked): - One shared database login is used for everyone, so permissions cannot be applied. - It copies each module's business rules into search, and they drift over time. - It assumes the same ProjectId means the same project in every database, which is not verified - BMS already works differently. Module readiness: - CMS is the strongest for real search value (contract name plus eleven long text fields). Action Meeting, DMS and Project are next. Suggested starting with Action Meeting and CMS, one for each half of the design. - Checklist / Work Permit is not ready - no title field and the content sits in child tables. Needs the module team to expose it properly first. - Most result links today are empty or point to pages that do not exist, and record IDs are not stable, so both have to be fixed for clicking a result to work. - No tenant column exists in any of the 17 databases, so multi-tenancy needs confirmation from the backend team. Blocked on the backend team: login token details, the permission model, at least one module search API contract, and which language the new service must be written in. Can start without them: extracting the query understanding code as a clean library, and building a set of real test queries with expected results to measure relevance.

## Hours by day
Worklog 21-24 Aug 2026 (Sat/Sun excluded) - 8 hours per weekday
Date | Day | Hours
21-Aug-2026 | Fri | 8
24-Aug-2026 | Mon | 8
Stories: 3 ¦ Total hours: 16 ¦ Component: AI/ML ¦ Type: Story ¦ Key: blank